## Sheet1
Number | Date Identified | Risk | Risk Category | Risk Probability | Cost To Correct (Hours) | Impact (Hours) | Risk Elimination Date | Risk Mitigation Plan | Cost of Mitigation Plan (Hours) | Residual Risk Probability | Residual Impact (Hours) | Mitigation Plan Cost + Residual Impact | Comments
R-001 | 2018-01-03 | Due to individual team member's personal schedules and weather conditions, we may not be able to meet in person as often as we would have liked. | Schedule | 0.3 | 0.5 | 0.15 | 2018-01-05 | 1. Create a google hangouts chatroom that allows online meetups and group collaboration. 2. Sign up for GroupMe text chatroom to establish group communication outside of scheduled hangouts meeting times. | 1 | 0.1 | 0.05 | 1.05
R-002 | 2018-01-26 | Due to the team's current skillset regarding website development, we may be unable to dynamically generate html elements on the property management dashboard to reflect the registered properties. | Technical | 0.6 | 16 | 9.6 | 2018-02-18 | 1. Create a less complex fallback design that would be easier to implement given our current web development skillset. 2. Research and develop test code for this alternate method to make sure that it can be implemented A.S.A.P. without any further issues. | 8 | 0.2 | 3.2 | 11.2
R-003 | 2018-01-26 | Due to the nature of the project, a private network is required for the sensors/assets to communicate with the MQTT Server and Website. As such, there is a chance that hosting all the servers on one raspberry pi might overload the system. | Programmatic Risk | 0.5 | 24 | 12 | 2018-03-14 | 1. Create a network infrastructure that includes the use of a second raspberry pi to alleviate the strain of hosting all networking components on one raspberry pi device. | 16 | 0.1 | 2.4 | 18.4
R-004 | 2018-03-10 | Due to the design of the Physical Model, the Raspberry Pi devices that will be housed within the attic may suffer from excessive heat build up and cause degraded system performance. | Programmatic Risk | 0.35 | 16 | 5.6 | 2018-03-14 | 1. Install a cooling fan in the attic to reduce the heat build-up. 2. Install a small heat extractor vent in the roof design that will help cool the system. 3. Add a servo to lift the roof of the attic for emergency cooling (also doubles as a way to quickly access the physical model's system components). | 16 | 0.1 | 1.6 | 17.6
R-005 | 2018-03-18 | Due to the electrical nature of the Physical Model, any loose or non-grounded wiring could lead to a short in the model's wiring circuit. | Programmatic Risk | 0.2 | 8 | 1.6 | 2018-03-28 | 1. Design a wire schematic that accounts for each sensor including the model's led lighting and then solder the wiring in place on the model to insure that there are no loose wires. | 16 | 0.1 | 0.8 | 0.9
R-006 | 2018-04-08 | Due to the nature of the number of sensors configured on each Arduino device, it was discovered that when commencing with serial reads and writes the system would confuse and overlap these writes with the wrong sensor and eventually brick itself in a loop. | Programmatic Risk | 0.8 | 24 | 19.2 | 2018-04-10 | 1. Add another Arduino microcontroller to the system to alleviate the overlapping of the serial reads and writes and avoid bricking the system. 2. Rearrange the devices on the wiring schematic to accomadate the additional Arduino on the circuit and to make sure that there is sapce on the model to house the device itself. | 24 | 0.2 | 4.8 | 5
|  |  |  | Totals (Hours) | 88.5 | 48.15 |  |  | 81 |  | 12.85 | 54.15
Note on H1: Jheryl Lezama: This date is tied directly to a milestone in the Project Plan (RLN).
Note on N1: Jheryl Lezama: Put in the "comments" column the changes that occur to any term during the course of the project and for every revision of the RMM. THIS IS AN ALTERNATIVE TO INDIVIDUAL COMMENTS WITHIN THE CELLS (AS I HAVE DONE IN THIS RMM). YOU DO NOT NEED BOTH.
Note on F3: Jheryl Lezama: The cost to correct (in hours) is equal to the estimated time it would take to setup alternate meeting times between the team members.
Note on J3: Jheryl Lezama: 1. Cost of mitigation plan (in hours) reflects the time it would take to setup a google hangouts chatroom, send out the link to each member and finally accounts for the time it takes to have members sign in and join. 2. This timeframe also reflects the time it would take to get each team member signed up for GroupMe chatrrom on their mobile devices.
Note on K3: Jheryl Lezama: Despite the Mitigation Plan there is still a 10% risk that team members may still be unable to meetup due to a last minute change in personal schedules.
Note on F5: Jheryl Lezama: 1. The cost to correct (in hours) is equal to the estimated time it would take to redesign an alternate user interface to reflect the changes that accompany the "landlord property registration" feature. 2. The redesign time takes into account the HTML, CSS, PHP and MySQL database development time that would accompany a complete system feature overhaul. 3. Time is based on a 8 hour work day, which in this case is 2 work days.
Note on J5: Jheryl Lezama: 1. The cost of mitigation plan (in hours) reflects the time it would take the group to draft out a fallback design including the HTML, CSS, PHP and MySQL database that would be used in the "Landlord property registration" feature.
Note on K5: Jheryl Lezama: Despite the Mitigation Plan there is still a 20% risk that the redesign may not meet course expectations in terms of a professional user interface.
Note on F7: Jheryl Lezama: 1. The cost to correct (in hours) is equal to the estimated time it would take to redesign the network infrastructure in order to avoid overloading the system. 2. The redesign time takes into account the time it would take to rescript the server configuration and create the actual servers. 3. Time is based on a 8 hour work day, which in this case is 3 work days.
Note on J7: Jheryl Lezama: 1. The cost of mitigation plan (in hours) reflects the time it would take to setup the second raspberry pi device to host the web server and MySQL database. 2. The time to script the configuration of the second raspberry pi device has been accounted for within this time frame. 3. Time is based on a 8 hour work day, which in this case is 2 days.
Note on K7: Jheryl Lezama: Despite the Mitigation Plan there is still a 10% risk that the new raspberry pi might run into complications with communicating with the rest of the system.
Note on F9: Jheryl Lezama: 1) The cost to correct (in hours) relates to the time it would take to implement a new layout for housing the raspberry pi devices. 2) Time is based on a 8 hour work day, which in this case is 2 work days.
Note on J9: Jheryl Lezama: 1) The cost of mitigation plan (in hours) reflects the time it would take to wire in the additional cooling fan and fabricate the cooling vent in roof assembly. 2) Time is based on a 8 hour work day, which in this case is 2 work days.
Note on K9: Jheryl Lezama: Despite the Mitigation Plan there is still a 10% risk that the new cooling system and implementation of the servo may not be enough to cool the system controlling the Physical Model.
Note on F11: Jheryl Lezama: 1) The cost to correct (in hours) relates to the time it would take to solder the wires in place. 2) Time is based on a 8 hour work day.
Note on J11: Jheryl Lezama: 1) The cost to correct (in hours) relates to the time it would take to draft out a wiring schematic and move the wires from the breadboard and solder to the model. 2) Time is based on a 8 hour work day, which in this case is 2 work days.
Note on K11: Jheryl Lezama: Despite the Mitigation Plan there is still a 10% risk that the issues with the wiring may persist.
Note on F13: Jheryl Lezama: 1) The cost to correct (in hours) relates to the time it would take to recode the Arduino logic controlling each of the various sensors. 2) Time is based on a 8 hour work day, which in this case 3 work days.
Note on J13: Jheryl Lezama: 1) The cost to correct (in hours) relates to the time it would take to wire and code the additional Arduino device. 2) Time is based on a 8 hour work day, which in this case is 3 work days.
Note on K13: Jheryl Lezama: Despite the Mitigation Plan there is still a 20% risk that there may be small issues with the serial reads and writes between the devices that degrade system performance, however it will not brick the system..
Note on M14: Jheryl Lezama: This is the project time reserve (hours).