## Sheet1
Number | Date Identified | Risk | Risk Category | Risk Probability | Cost To Correct (Hours) | Impact (Hours) | Risk Elimination Date | Risk Mitigation Plan | Cost of Mitigation Plan (Hours) | Residual Risk Probability | Residual Impact (Hours) | Mitigation Plan Cost + Residual Impact | Comments
R-001 | 2018-01-03 | Due to personal schedules and weather conditions, we may not be able to meet in person as often as we would have liked. | Schedule | 0.25 | 0.5 | 0.125 | 2018-01-05 | 1. Create a google hangouts chatroom that allows online meetups and group collaboration | 1 | 0.1 | 0.05 | 1.05
R-002 | 2018-01-26 | Due to our current skill set with regards to web development, we may be unable to genrate html elements on the main page to accompany the landlord property registration feature. | Technical | 0.5 | 16 | 8 | 2018-02-18 | 1. Create a less complex fallback design that would be easier to implement given our current web development skillset. | 8 | 0.2 | 3.2 | 11.2
R-003 | 2018-01-26 | Due to the nature of the project, a private network is required for the sensors/assets to communicate with the MQTT Server and Website. As such, there is a chance that hosting all the servers on one raspberry pi might overload the system. | Programmatic Risk | 0.5 | 24 | 12 | 2018-03-14 | 1. Create a network infrastructure that includes the use of a second raspberry pi to alleviate the strain of hosting all networking components on one raspberry pi device. | 16 | 0.1 | 2.4 | 18.4
|  |  |  | Totals (Hours) | 40.5 | 20.125 |  |  | 25 |  | 5.65 | 30.65
Note on H1: Preston Brooks: This date is tied directly to a milestone in the Proect Plan (RLN).
Note on M1: Preston Brooks: This is the Cost of the Mitigation Plan + Residual Impact.
Note on N1: Jheryl Lezama: Put in the "comments" column the changes that occur to any term during the course of the project and for every revision of the RMM. THIS IS AN ALTERNATIVE TO INDIVIDUAL COMMENTS WITHIN THE CELLS (AS I HAVE DONE IN THIS RMM). YOU DO NOT NEED BOTH.
Note on F3: Jheryl Lezama: The cost to correct (in hours) is equal to the estimated time it would take to setup alternate meeting times between the team members.
Note on J3: Jheryl Lezama: 1. Cost of mitigation plan (in hours) reflects the time it would take to setup a google hangouts chatroom, send out the link to each member and finally accounts for the time it takes to have members sign in and join.
Note on K3: Jheryl Lezama: Despite the Mitigation Plan there is still a 10% risk that team members may still be unable to meetup due to a last minute change in personal schedules.
Note on F5: Jheryl Lezama: 1. The cost to correct (in hours) is equal to the estimated time it would take to redesign an alternate user interface foruse with the "landlord property registration" feature. 2. The redesign time takes into account the HTML, CSS, PHP and MySQL database development time that would accompany a complete system feature overhaul. 3. Time is based on a 8 hour work day.
Note on J5: Jheryl Lezama: 1. The cost of mitigation plan (in hours) reflects the time it would take the group to draft out a fallback design including the HTML, CSS, PHP and MySQL database that would be used in the "Landlord property registration" feature.
Note on K5: Jheryl Lezama: Despite the Mitigation Plan there is still a 20% risk that the redesign may not meet course expectations in terms of a professional user interface.
Note on F7: Jheryl Lezama: 1. The cost to correct (in hours) is equal to the estimated time it would take to redesign the network infrastructure in order to avoid overloading the system. 2. The redesign time takes into account the time it would take to rescript the server configuration and create the actual servers. 3. Time is based on a 8 hour work day.
Note on J7: Jheryl Lezama: 1. The cost of mitigation plan (in hours) reflects the time it would take to setup the second raspberry pi device to host the web server and MySQL database. 2. The time to script the configuration of the second raspberry pi device has been accounted for within this time frame. 3. Time is based on a 8 hour work day.
Note on K7: Jheryl Lezama: Despite the Mitigation Plan there is still a 10% risk that the new raspberry pi might run into complications with communicating with the rest of the system.
Note on M9: Jheryl Lezama: This is the project time reserve (hours).