## Sheet1
Connected Housing Solutions Project Plan 2018
WBS | WBS | Task Name | Duration (hrs) | Start | Finish | Predecessor | Comments
1 |  | Home Automation |  | 2018-01-02 | 2018-04-18
1.1 |  | Project Start | 0 hrs | Milestone
1.2 |  | Management
| 1.2.1 | Conduct Project Meetings | 3 hrs | Reoccuring M,W,F,Sat | 2018-04-19
| 1.2.2 | Conduct Project Review | 2 hrs | 2018-01-03 | 2018-01-09
| 1.2.3 | Develop RMM Matrix | 2 hrs | 2018-01-03 | 2018-01-09
| 1.2.4 | Finalize Project Plan | 2 hrs | 2018-01-09 | 2018-01-09
| 1.2.5 | Brief Project Team | 1 hrs | 2018-01-03 | 2018-01-03
1.3 |  | Environment
| 1.3.1 | Configure development team laptops | 4 hrs | 2018-01-03 | 2018-01-09
| 1.3.2 | Configure Github repository | 1 hrs | 2018-01-03 | 2018-01-09 | 1.3.1
| 1.3.3 | Configure Raspberry Pi | 2 hrs | 2018-03-07 | 2018-03-14
| 1.3.4 | Configure MQTT Server | 2 hrs | 2018-03-14 | 2018-03-21 | 1.3.4
| 1.3.5 | Configure MySQL Server | 4 hrs | 2018-03-28 | 2018-04-04 | 1.3.4
| 1.3.6 | Configure Arduinos | 4 hrs | 2018-02-07 | 2018-02-14
| 1.3.7 | Complete Environment | 4 hrs | 2018-02-21 | 2018-02-28 | 1.3.2
1.4 |  | Requirements
| 1.4.1 | Extract system level requirements from OpCon | 2 hrs | 2018-01-03 | 2018-01-09
| 1.4.2 | Refine and clarify initial system-level requirements | 4 hrs | 2018-01-03 | 2018-01-09
| 1.4.3 | Obtain signoff on preliminary requirements | 3 hrs | 2018-01-03 | 2018-01-09
| 1.4.4 | Draft user stories for each system-level requirement | 3 hrs | 2018-01-03 | 2018-01-09 | 1.4.1
1.5 |  | Design & Implementation
| 1.5.1 | Finalize User Story Requirements | 10 hrs | 2018-01-04 | 2018-01-09
| 1.5.2 | Conduct Test of System Framework | 8 hrs | 2018-01-04 | 2018-01-09
| 1.5.3 | Develop Mobile Application | 40 hrs | 2018-01-09 | 2018-03-28
| 1.5.4 | Develop Web Application | 40 hrs | 2018-01-09 | 2018-03-28
| 1.5.5 | Develop Arduino Logic Code | 40 hrs | 2018-01-09 | 2018-03-28
| 1.5.6 | Integrate MQTT Server | 20 hrs | 2018-01-09 | 2018-03-28 | 1.3.3 | Integratation relates to having the server communicating with the rest of the system vs. configuration which includes the powershell scripting of the server itself and implementing network security measures.
| 1.5.7 | Integrate Raspberry Pi | 20 hrs | 2018-01-09 | 2018-03-28 | 1.3.3
| 1.5.8 | Integrate MySQL Server | 20 hrs | 2018-01-09 | 2018-03-28 | 1.3.3
1.6 |  | Assessment
| 1.6.1 | Conduct weekly RMM Review | 2 hrs | Reoccuring weekly
| 1.6.2 | Deliver Bi-Weekily Sprint Progress Reports | 2 hrs | Reoccuring every 2 weeks
1.7 |  | Deployment
| 1.7.1 | Conduct software fixes from user field testing | 20hrs | 2018-04-10 | 2018-04-12
| 1.7.2 | Deliver final release | 4 hrs | 2018-04-19 | 2018-04-19
| 1.7.3 | Obtain Project Signoff | 4 hrs | 2018-04-19 | 2018-04-19
| 1.7.4 | Close Project | 0 hrs | Milestone